{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["封面","度量项指标","分析项指标"],"not_rendered":{"external_links":3,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"封面","index":0,"n_rows":23,"n_cols":8,"rows_kept":23,"merged":[[1,0,2,7],[4,0,4,7],[21,2,21,4],[22,2,22,4],[23,2,23,4],[24,2,24,4]],"flags":["formulas_cached_only"]}
[]
["上海柏维信息技术有限公司"]
[]
[]
["度量指标"]
[]
[]
[{"$nulls":4},"文件编号：","MPM_Index"]
[{"$nulls":4},"版本：","1.0"]
[{"$nulls":4},"用户：","内部员工"]
[{"$nulls":4},"分类：","模板"]
[]
[{"$nulls":4},"状态：","正式发布"]
[{"$nulls":4},"密级：","内部公开"]
[]
["文档信息"]
["创建日期：","2023-3-12",null,"更新日期：2023-3-12"]
["编制：","杨国强\n",null,"生效日期：2023-3-12"]
["审核：","薛金元\n",null,"批准：胡志军\n"]
[]
["修订文档历史记录"]
["日期","版本号","修订说明",null,null,"修订人","审核人","批准人"]
["2023-3-12","1.0","创建",null,null,"杨国强\n","薛金元\n","胡志军\n"]

{"sheet":"度量项指标","index":1,"n_rows":16,"n_cols":14,"rows_kept":16,"merged":[[1,1,1,13],[2,1,2,2],[8,1,8,13],[9,1,9,2],[10,1,12,1],[13,1,14,1]],"flags":["formulas_cached_only"]}
[]
[null,"组织级-度量项指标"]
[null,"度量目标",null,"度量项","定义及用途","单位","计算公式","数据类型","数据格式","采集源","存储方法","报告方法","变更控制","存取控制"]
[null,"提高项目组估算能力","1、阶段进度偏差-10%至+10%\n2、成本偏差控制在-10%至+10%\n3、工作量偏差控制在-10%至+10%\n4、编码阶段开始后规模偏差控制在-10%至+10%","项目历史数据\n项目实施数据","了解各个项目的规模，工作量，进度，生产率，进行分析对比","无","无","不限","不限","项目《度量数据表》","《组织度量表》","将《组织度量表》作为附件或整合在EPG周会议记录中，通过会议、电子邮件等方式报告给公司高层和项目经理。","EPG组长审批","EPG组长可写，项目经理以上人员及项目组成员可读。"]
[null,"提高产品质量","所有阶段缺陷密度小于0.5","缺陷数、问题个数","对有关质量数据进行分析，尽量在产品交付前检查出更多缺陷，预防缺陷发生，提高产品质量。","个","无","不限","不限","项目《度量数据表》","《组织度量表》","将《组织度量表》作为附件或整合在EPG周会议记录中，通过会议、电子邮件等方式报告给公司高层和项目经理。","EPG组长审批","EPG组长可写，项目经理以上人员及项目组成员可读。"]
[null,"提高过程改进工作效果","过程改进建议采纳率大于10%","过程改进建议","了解不同对象对于过程改进工作的意见建议","个","无","不限","不限","项目《里程碑状态报告》","《过程改进建议表》","将《过程改进建议表》作为附件或整合在EPG周会议记录中，通过会议、电子邮件等方式报告给公司高层和项目经理。","EPG组长审批","EPG组长可写，项目经理以上人员及项目组成员可读。"]
[]
[]
[null,"项目级-度量项指标"]
[null,"度量目标",null,"度量项","定义及用途","单位","计算公式","数据类型","数据格式","采集源","存储方法","报告方法","变更控制","存取控制"]
[null,"提高估算精确度","工作量偏差控制在-10%至+10%","工作量","了解项目各种过程的工作量","人日","|计划-实际|/计划","正实数","保留一位小数","从《项目周报》中收集","度量数据表","将《度量数据表》作为附件或整合在周会议记录中，通过会议、电子邮件等方式报告给部门经理和项目组。","项目经理审批","项目经理可写，项目经理以上人员及项目组成员可读。"]
[null,null,"编码阶段开始后规模偏差控制在-10%至+10%","规模","了解项目的实际规模","功能点/画面数/代码行","无","正实数","保留一位小数","从《项目估算书》中收集估计规模，从《结项报告》中收集实际规模","同上","同上","同上","同上"]
[null,null,"阶段进度偏差-10%至+10%","进度","了解项目的实际进度偏差","天","|计划-实际|/计划","正整数","不限","从里程碑状态报告中收集","同上","同上","同上","同上"]
[null,"提高产品质量和掌握缺陷分布","项目发生问题控制在15个/项目之内","问题","了解项目中发生问题的个数、类型、严重程度及分布","个","无","正整数","不限","从《问题管理一览表》中收集","同上","将度量数据表作为附件或整合在里程碑状态报告、《结项报告》中发送给部门经理和项目组","同上","同上"]
[null,null,"所有阶段缺陷密度小于0.5","测试BUG","了解系统测试的缺陷个数、类型、严重程度及分布","个","无","正整数","不限","从测试报告中收集","同上","同上","同上","同上"]
[null,"降低成本","成本偏差控制在-10%至+10%","项目成本","了解各项目各阶段所花费成本","元","无","正实数","保留一位小数","从《项目估算书》《里程碑状态报告》中收集","同上","同上","同上","同上"]

{"sheet":"分析项指标","index":2,"n_rows":15,"n_cols":14,"rows_kept":15,"merged":[[0,1,0,13],[1,1,1,2],[1,5,1,6],[2,5,2,6],[3,5,3,6],[4,5,4,6],[10,1,10,13],[11,1,11,2],[11,5,11,6],[12,5,12,6],[13,5,13,6],[14,5,14,6]],"flags":["formulas_cached_only"]}
[null,"组织级-分析项指标"]
[null,"度量目标",null,"分析项","意义","计算公式",null,"数据类型","数据格式","分析方法","存储方法","报告方法","变更控制","存取控制"]
[null,"提高项目组估算能力","1、阶段进度偏差-10%至+10%\n2、成本偏差控制在-10%至+10%\n3、工作量偏差控制在-10%至+10%\n4、编码阶段开始后规模偏差控制在-10%至+10%","各个项目的规模，工作量，进度，生产率的估算与实际的偏差","对过程改进实施后项目组估算能力的分析","偏差/估算值",null,"百分比","保留一位小数","与历史项目进行对比分析","组织级度量数据表","由项目经理在结项后将度量的数据提交给EPG组长，由EPF组长对数据进行分析和更新于《组织度量数据表》","EPG组长审批","EPG组长可写；项目经理及EPG成员可读；"]
[null,"提高产品质量","所有阶段缺陷密度小于0.5","各项目的缺陷率","对有关质量数据进行分析，尽量在产品交付前检查出更多缺陷，预防缺陷发生，提高产品质量。分析项目组缺陷发现的能力","各阶段缺陷/总缺陷",null,"百分比","保留一位小数","与历史项目进行对比分析","组织级度量数据表","由项目经理在结项后将度量的数据提交给EPG组长，由EPF组长对数据进行分析和更新于《组织度量数据表》","EPG组长审批","EPG组长可写；项目经理及EPG成员可读；"]
[null,"提高过程改进工作效果","过程改进建议采纳率大于10%","过程改进建议","收集过程改进建议个数，掌握和了解过程改进活动状态和过程改进的实施力度与员工的参与程度","各个角色过程改进建议条数/总建议条数",null,"百分比","保留一位小数","与历史项目进行对比分析","组织级度量数据表","由项目经理在结项后将度量的数据提交给EPG组长，由EPF组长对数据进行分析和更新于《组织度量数据表》","EPG组长审批","EPG组长可写；项目经理及EPG成员可读；"]
[]
[]
[]
[]
[]
[null,"项目级-分析项指标"]
[null,"度量目标",null,"分析项","意义","计算公式",null,"数据类型","数据格式","分析方法","存储方法","报告方法","变更控制","存取控制"]
[null,"提高估算精确度","工作量偏差控制在-10%至+10%\n编码阶段开始后规模偏差控制在-10%至+10%\n阶段进度偏差-10%至+10%\n成本偏差控制在-10%至+10%","生产率","了解项目的生产率","规模/工作量",null,"正实数","保留一位小数","与历史项目对比","度量数据表","将度量数据表作为附件或整合在《结项报告》中发送给部门经理和项目组","项目经理审批","项目经理可写；项目经理以上人员及项目组成员可读。"]
[null,"提高产品质量和掌握缺陷分布","所有阶段缺陷密度小于0.5","缺陷密度","了解产品的缺陷情况","缺陷个数/规模",null,"正实数","保留一位小数","与历史项目对比","同上","同上","同上","同上"]
[null,"提高项目策划的能力","工作量偏差控制在-10%至+10%\n编码阶段开始后规模偏差控制在-10%至+10%\n阶段进度偏差-10%至+10%\n成本偏差控制在-10%至+10%","项目偏差率","从进度、成本两方面进行项目监控的主要依据","|计划-实际|/计划",null,"百分比","保留一位小数","计划与实际的对比","同上","将度量数据表作为附件或整合在《项目周报》、里程碑状态报告中，并通过会议、电子邮件等方式报告给部门经理和项目组。","同上","同上"]